## Sprint 1 Backlog
Smart-Attend ¦ Sprint 1 Backlog (MVP)
Sprint Duration: 2 Weeks ¦ Goal: Build the MVP with Login, Geo-fencing & Core UI
Task ID | User Story (As a..., I want..., So that...) | Role | Priority | Est. Hours | Story Points | Assigned To | Sprint | Status
US01 | As a student, I want to login via university ID so I can access my profile. | Student | High | 4 | 3 | Dev A | Sprint 1 | To Do
US02 | As a teacher, I want to view a real-time list of present students. | Teacher | High | 6 | 5 | Dev B | Sprint 1 | To Do
US03 | As a system, I want to detect if a student is within 10m of the classroom. | System | High | 8 | 8 | Dev C | Sprint 1 | To Do
US04 | As a student, I want a notification when my attendance is marked. | Student | Medium | 3 | 2 | Dev A | Sprint 1 | To Do
US05 | As an admin, I want to manually override attendance for technical errors. | Admin | Low | 4 | 3 | Dev B | Sprint 1 | To Do
US06 | As a student, I want to see my attendance history so I can track my record. | Student | Medium | 3 | 2 | Dev C | Sprint 1 | To Do
US07 | As a teacher, I want to set the classroom geo-fence coordinates on a map. | Teacher | High | 5 | 5 | Dev A | Sprint 1 | To Do
US08 | As a student, I want to see a confirmation screen when I enter the classroom zone. | Student | Medium | 2 | 1 | Dev B | Sprint 1 | To Do
TOTAL

## Sprint 2 Backlog
Smart-Attend ¦ Sprint 2 Backlog (Biometric Update)
Sprint Duration: 2 Weeks ¦ Goal: Integrate Face ID, Refine Dashboard, Close Sprint 1 Feedback
Task ID | User Story (As a..., I want..., So that...) | Role | Priority | Est. Hours | Story Points | Assigned To | Sprint | Status
US09 | As a student, I want to verify my identity via Face ID so proxy attendance is prevented. | Student | High | 8 | 8 | Dev A | Sprint 2 | To Do
US10 | As a system, I want to require both geo-fence and Face ID before finalizing attendance. | System | High | 6 | 5 | Dev C | Sprint 2 | To Do
US11 | As a teacher, I want a weekly attendance summary report exportable as CSV. | Teacher | High | 5 | 5 | Dev B | Sprint 2 | To Do
US12 | As a student, I want Face ID to work even if the app is in background mode. | Student | Medium | 4 | 3 | Dev A | Sprint 2 | To Do
US13 | As an admin, I want to filter attendance reports by course, date, and student. | Admin | Medium | 4 | 3 | Dev B | Sprint 2 | To Do
US14 | As a system, I want biometric data processed on-device only — never stored on servers. | System | High | 5 | 5 | Dev C | Sprint 2 | To Do
US15 | As a teacher, I want to receive an alert if a student fails Face ID verification repeatedly. | Teacher | Low | 3 | 2 | Dev A | Sprint 2 | To Do
TOTAL

## Product Backlog
Smart-Attend ¦ Product Backlog (Full Feature List)
Epic | User Story | Priority | Story Points | Assigned Sprint | Status | Notes
Authentication | Student login via University ID | High | 3 | Sprint 1 | Planned | SSO/LDAP integration
Geo-fencing | Detect student within 10m of classroom | High | 8 | Sprint 1 | Planned | GPS + Geofence API
Geo-fencing | Teacher sets classroom coordinates | High | 5 | Sprint 1 | Planned | Map UI required
Notifications | Push notification on attendance marked | Medium | 2 | Sprint 1 | Planned | FCM / APNs
Dashboard | Teacher: real-time present/absent list | High | 5 | Sprint 1 | Planned | WebSocket refresh
Admin | Manual attendance override | Low | 3 | Sprint 1 | Planned | Audit log required
History | Student: view attendance history | Medium | 2 | Sprint 1 | Planned
UI | Confirmation screen on geo-fence entry | Medium | 1 | Sprint 1 | Planned
Biometrics | Face ID verification on attendance | High | 8 | Sprint 2 | Backlog | On-device only
Biometrics | Require geo-fence + Face ID for confirmation | High | 5 | Sprint 2 | Backlog
Biometrics | Biometric data never stored server-side | High | 5 | Sprint 2 | Backlog | Security requirement
Biometrics | Face ID in background mode | Medium | 3 | Sprint 2 | Backlog | iOS/Android specific
Reporting | Weekly attendance CSV export | High | 5 | Sprint 2 | Backlog
Reporting | Filter reports by course/date/student | Medium | 3 | Sprint 2 | Backlog
Alerts | Alert teacher on repeated Face ID failures | Low | 2 | Sprint 2 | Backlog